## Summary
IT Executive Activity Dashboard
Coverage: Annie Insights Web, iSmartOffice Web App, Mobile App, QA Testing, BigData, Infrastructure, and Executive Reporting
KPI | Value | Target / Threshold | Notes | KPI | Value | Target / Threshold | Notes
Total Activities | 45 | All active items | Portfolio scope | On-Time or Closed % | 56% | >= 85% | Schedule health
Completed Activities | 21 | Increasing weekly | Done status | QA Pass Rate | 100% | >= 90% | Passed vs failed tests
Open Activities | 24 | Controlled backlog | Not yet closed | Critical Items | 1 | Visible to management | Critical priority
Blocked / Risk Items | 8 | Target: 0 | Requires executive attention | BigData Pipelines | 11 | All tracked | Data engineering scope
Avg Progress | 41% | >= 70% | Across all activities | Over-Capacity Teams | 2 | Target: 0 | Resource risk

## iSmartOffice Product
Patient |  | Clinic |  | Provider |  |  | Web Clinic
Feature | Ok? | Feature | Ok? | Feature | Ok? | Error | Feature | Ok? | Error
Sign Up | TRUE | Language Change | TRUE | Login | TRUE |  | Login | TRUE
Login | TRUE | Login QR | TRUE | Language Change | TRUE |  | Dashboard
Clinic Group | TRUE | Login Typing | TRUE | Schedule | TRUE |  | Add Clinic Pop Up | TRUE
Language Change | TRUE |  |  | My Calendar |  |  | Calendar | TRUE
DR. ANNIE | TRUE | Appointment Incoming | TRUE | Schedule List | FALSE | Need to update Front End | Appointment List | TRUE
Submit Case | TRUE | Accept/Reject | TRUE | Date Feature | TRUE |  | Status Widget | TRUE
Camera | TRUE |  |  | DR. ANNIE |  |  | Profile
Upload | TRUE | Provider Incoming | TRUE | New Case Incoming | TRUE |  | Edit User Profile | TRUE
Complete Case | TRUE | Accept/Reject | TRUE | View Result | TRUE |  | Membership | TRUE
Release Case | TRUE |  |  | Confirm OK/ Overwrite | TRUE |  | Clinic Setup
View Result | TRUE | QR Patient Visit | TRUE | Reviewed Case | TRUE |  | My Clinic List | TRUE
Find Clinic | TRUE | QR Validate Best Deal | TRUE | WorkHub |  |  | Clinic Profile | TRUE
Enter Address | TRUE |  |  | Membership | TRUE |  | Clinic Member | TRUE
Select Date | TRUE | History | TRUE | Accept/Reject | TRUE |  | Clinic Chair | TRUE
Select Treatment | TRUE |  |  | Schedule Approvals | TRUE |  | Operating Schedule | TRUE
BVI | TRUE | Email Notif | TRUE | Accept/Reject | TRUE |  | Treatment Pricing | TRUE
Find Clinic | TRUE | Push Notif | TRUE | Vacant Schedules | TRUE |  | Operation
Pick Hours | TRUE |  |  | Apply | TRUE |  | Appointment List | TRUE
Book Appointment | TRUE |  |  | Emergency | FALSE | Need to update API parameter | Discounted Slot | TRUE
Best Deal | TRUE |  |  | Apply | FALSE | Need to update API parameter | Doctor Schedule | TRUE
Best Deal List | TRUE |  |  | My Application | TRUE |  | Vacant Schedule | TRUE
Coupon Purchase | TRUE |  |  | Profile | TRUE |  | Dental Evaluation | TRUE
Appointment | TRUE |  |  | Change Password | TRUE |  | List | TRUE
Appointment List | TRUE |  |  | Past Visits | TRUE |  | Assign Doctor | TRUE
Zoom Teledentistry | TRUE |  |  | Email Notif | TRUE |  | Transfer to DR. ANNIE | FALSE | Integration still not working
Prepaid Appointment | TRUE |  |  | Push Notif | TRUE |  | Best Deal Added | TRUE
Cancel Appointment | TRUE | [5 empty] | Best Deal Paid | TRUE
[7 empty] | Treatment Length Estimator | TRUE
Help & Guide | TRUE | [5 empty] | TBL Report | FALSE
Dental History | TRUE | [5 empty] | Legal Consent | TRUE
Refer a Friend | TRUE | [5 empty] | Login Code for Clinic App | TRUE
Email Notif | TRUE | [5 empty] | Help | TRUE
Push Notif | TRUE | [5 empty] | Tawkto | FALSE | Still not implemented
[7 empty] | Log Out | TRUE

## Enterprise Apps
AllCare Ortho |  | FMBO |  | Sphinx
Feature | Ok? | Feature | Ok? | Feature | Ok?
Login | TRUE | Login | TRUE | Login | TRUE
Language Change | TRUE | Language Change | TRUE | Language Change | TRUE
DR. ANNIE | TRUE | DR. ANNIE | TRUE | DR. ANNIE | TRUE
Submit Case | TRUE | Submit Case | TRUE | Submit Case | TRUE
Camera | TRUE | Camera | TRUE | Camera | TRUE
Upload | TRUE | Upload | TRUE | Upload | TRUE
Complete Case | TRUE | Complete Case | TRUE | Complete Case | TRUE
Release Case | TRUE | Release Case | TRUE | Release Case | TRUE
View Result | TRUE | View Result | TRUE | View Result | TRUE
Find Clinic | TRUE | Find Clinic | TRUE | Find Clinic | TRUE
Enter Address | TRUE | Enter Address | TRUE | Enter Address | TRUE
Select Date | TRUE | Select Date | TRUE | Select Date | TRUE
Select Treatment | TRUE | Select Treatment | TRUE | Select Treatment | TRUE
BVI | TRUE | BVI | TRUE | BVI | TRUE
Find Clinic | TRUE | Find Clinic | TRUE | Find Clinic | TRUE
Pick Hours | TRUE | Pick Hours | TRUE | Pick Hours | TRUE
Book Appointment | TRUE | Book Appointment | TRUE | Book Appointment | TRUE
Best Deal | TRUE | Best Deal | TRUE | Best Deal | TRUE
Best Deal List | TRUE | Best Deal List | TRUE | Best Deal List | TRUE
Coupon Purchase | TRUE | Coupon Purchase | TRUE | Coupon Purchase | TRUE
Appointment | TRUE | Appointment | TRUE | Appointment | TRUE
Appointment List | TRUE | Appointment List | TRUE | Appointment List | TRUE
Zoom Teledentistry | TRUE | Zoom Teledentistry | TRUE | Zoom Teledentistry | TRUE
Prepaid Appointment | TRUE | Prepaid Appointment | TRUE | Prepaid Appointment | TRUE
Cancel Appointment | TRUE | Cancel Appointment | TRUE | Cancel Appointment | TRUE
| TRUE |  | TRUE |  | TRUE
Help & Guide | TRUE | Help & Guide | TRUE | Help & Guide | TRUE
Dental History | TRUE | Dental History | TRUE | Dental History | TRUE
Refer a Friend | TRUE | Refer a Friend | TRUE | Refer a Friend | TRUE
Email Notif | TRUE | Email Notif | TRUE | Email Notif | TRUE
Push Notif | TRUE | Push Notif | TRUE | Push Notif | TRUE
Push Notif | TRUE | Push Notif | TRUE | Push Notif | TRUE

## Annie Insights Product
Login Page |  | Homescreen |  | Add New Patient |  | Time Points |  | AI-Findings |  | Patient Digitize |  | Report |  | Patient Information |  | New Features
Login SSO | TRUE | Active Patient | TRUE | Doctor Name | TRUE | Create Time Points | TRUE | Intra Oral | TRUE | API Template |  | Generate Report |  | Case ID | TRUE | Bulk Upload | Untested
Log In | TRUE | Archive Patient | TRUE | Patient Name | TRUE | Add More Time Points | TRUE | Extra Oral | TRUE | Points | TRUE | Standart | TRUE | Selected Time Points | TRUE | Diagram | Untested
Log Out | TRUE | Search Patient | TRUE | Patient Email and Phone | TRUE | Consult Date |  | Panoramic Radiographs | TRUE | Cephalometric | TRUE | Standart Plus | TRUE | Porgress Bar | TRUE | HLD Report | Untested
|  |  |  | Patient Birth Date | TRUE | Lateral X-Ray Date |  | Cephalometric |  | Dental Arch | TRUE | Complete | TRUE | Menu |  | Panoramic Radiograph | Untested
|  | Patient List Information |  | Patient Sex | TRUE | List Time Point Consistency |  | Verify Lateral | TRUE | Reset Process | TRUE | Auto-Correct Function | TRUE | Edit Patient | TRUE
|  | Patient | TRUE | Patient Ethnicity | TRUE | Images Upload | TRUE | Verify Frontal | TRUE | Contrast - Brightness | TRUE |  |  | Share Patient | TRUE
|  | Profile | TRUE | Patient Height | TRUE | Intra Oral | TRUE | Dental Arch |  | Zoom In/Zoom Out | TRUE | Report (DNN & PDF) |  | Transfer Patient | TRUE
|  | Timepoint | TRUE |  |  | Extra Oral | TRUE | Verify Upper | TRUE | Points Editing/drag the point | TRUE | Dental Evaluation | TRUE | Delete Patient | TRUE
|  | Progress | TRUE | HIPA Checklist | TRUE | Dental Chart | TRUE | Verify Lower | TRUE |  |  | Problem List | TRUE | Reset Time Point | TRUE
|  | Action | TRUE | Cancel/Submit | TRUE | X-Ray Radiographs | TRUE |  |  |  |  | Treatment Rationale | TRUE | Delete Time Point | TRUE
|  | Share Patient | TRUE |  |  |  |  | Verify function | TRUE |  |  | Case Evaluation | TRUE
|  | Transfer | TRUE |  |  |  |  | Upload/Edit/Download | TRUE | Status API Log in Back End | TRUE | Dental Findings | TRUE
|  | Archive | TRUE | [8 empty] | Skeletal Findings | TRUE
|  | Delete | TRUE |  |  |  |  | Patient Digitize | TRUE |  |  | Tracing Measurements | TRUE
[9 empty] | ➡️ |  |  | Sequences Worksheet | TRUE
|  | Add New Patient | TRUE | [8 empty] | Full Comprehensive | TRUE
➡️
Activity ID | Product | Activity / Task | Team | Priority | Status | Start Date | Due Date | Schedule Flag
ACT-003 | Annie Insights Web | robust testing scenario for Annie and iSmartOffice | AI-Web | High | In Progress | 2026-05-21 | 2026-05-28 | Overdue
ACT-010 | Annie Insights Web | dashboard annie user | AI-Web | Medium | Blocked | 2025-08-25 | 2025-09-01 | Overdue
ACT-015 | Annie Insights Web | Add timepoint UI UX | AI-Web | Medium | Done | 2026-04-13 | 2026-04-20 | Closed
ACT-019 | Annie Insights Web | API Report for Annie & Public Service | AI-Web | Medium | In Progress | 2026-05-12 | 2026-05-19 | Overdue
ACT-029 | Annie Insights Web | Source code takeover (90% complete) | AI-Web | Medium | In Progress | 2026-05-20 | 2026-06-15 | Due Soon
ACT-030 | Annie Insights Web | Deploy Angular and Backend Updates | AI-Web | Medium | Done | 2026-05-20 | 2026-06-10 | Closed
ACT-031 | Annie Insights Web | Auth0 Change Password Feature | AI-Web | Medium | Done | 2026-05-20 | 2026-06-10 | Closed
ACT-032 | Annie Insights Web | Popup Terms of Use & Privacy Policy | AI-Web | Low | Done | 2026-05-20 | 2026-06-10 | Closed
ACT-033 | Annie Insights Web | Birthdate & Age Validation | AI-Web | Medium | Done | 2026-05-20 | 2026-06-10 | Closed
ACT-034 | Annie Insights Web | UI/UX Bug Fixes | AI-Web | Medium | Done | 2026-05-20 | 2026-06-10 | Closed
ACT-035 | Annie Insights Web | Test Reporting Engine Buttons | AI-Web | Medium | Testing | 2026-06-10 | 2026-06-17 | Due Soon

## Big Data
Pipeline ID | Dataset / Subject | Product | Records / Volume | Data Quality % | Last Run | Next Run | Status
BD-001 | robust testing scenario for Annie and iSmartOffice | Annie Insights Web | 10000 | 95% | 2026-05-21 |  | Planned
BD-002 | Intra Oral Photos | Annie Insights Web | 228410 | 95% | 2026-06-04 |  | Completed
BD-003 | X-Rays / Radiographs | Annie Insights Web | 308007 | 98% | 2026-06-04 |  | Completed
BD-004 | 3D Scans (STL) | Annie Insights Web | 22908 | 97% | 2026-06-04 |  | Completed
BD-005 | Antioch Patient Archive | iSmartOffice Web App | 2752 | 96% | 2026-06-04 |  | Completed
BD-006 | Grayslake Patient Archive | iSmartOffice Web App | 1840 | 96% | 2026-06-04 |  | Completed
BD-007 | Gurnee Patient Archive | iSmartOffice Web App | 3120 | 96% | 2026-06-04 |  | Completed
BD-008 | Invisalign Refine | iSmartOffice Web App | 1894 | 99% | 2026-06-04 |  | Completed
BD-009 | Invisalign Verified | iSmartOffice Web App | 4120 | 99% | 2026-06-04 |  | Completed
BD-010 | iTero Invisalign Verified | iSmartOffice Web App | 12050 | 99% | 2026-06-04 |  | Completed
BD-011 | 1600 Dolphin case processing | Annie Insights Web | 1600 | 96% | 2026-05-06 |  | Completed

## Activity Log
Activity ID | Product | Activity / Task | Team | Priority | Status | Start Date | Due Date | Schedule Flag
ACT-001 | Shared Platform | Auth0 Integration | AI-Web | Medium | Done | 2026-05-12 | 2026-05-19 | Closed
ACT-002 | Infrastructure / DevOps | Migrate All Wordpress Site to HCDS Azure Multisite | Infra | Low | Done | 2025-07-07 | 2025-07-14 | Closed
ACT-003 | Annie Insights Web | robust testing scenario for Annie and iSmartOffice | AI-Web | High | In Progress | 2026-05-21 | 2026-05-28 | Overdue
ACT-004 | Shared Platform | finalize mock up pivoting | AI-Web | High | In Progress | 2026-05-21 | 2026-05-28 | Overdue
ACT-005 | iSmartOffice Web App | AI - Web - Change Doctor ID to be Doctor Name | AI-Web | Medium | Blocked | 2025-06-16 | 2025-06-23 | Overdue
ACT-006 | Shared Platform | AI - Web - Display last 3 patients after login | AI-Web | Medium | Blocked | 2025-07-28 | 2025-08-04 | Overdue
ACT-007 | Shared Platform | AI - Web - Add action button to Case Summary | AI-Web | Medium | Blocked | 2025-07-28 | 2025-08-04 | Overdue
ACT-008 | Shared Platform | add quick access sidebars | AI-Web | Medium | Blocked | 2025-08-25 | 2025-09-01 | Overdue
ACT-009 | Shared Platform | active user menu | AI-Web | Medium | Blocked | 2025-08-25 | 2025-09-01 | Overdue
ACT-010 | Annie Insights Web | dashboard annie user | AI-Web | Medium | Blocked | 2025-08-25 | 2025-09-01 | Overdue
ACT-011 | Shared Platform | AI - Transform - Use Parallax Calculation for Upper / Lower | AI-Web | Medium | Planned | 2026-01-15 | 2026-02-28 | Overdue
ACT-012 | Shared Platform | Verification process | AI-Web | Medium | Planned | 2026-03-29 | 2026-04-05 | Overdue
ACT-013 | Shared Platform | Credit notification | AI-Web | Medium | Done | 2026-03-29 | 2026-04-05 | Closed
ACT-014 | Shared Platform | Mapping bug fixes | Clinic-Web | Medium | Done | 2026-04-01 | 2026-04-08 | Closed
ACT-015 | Annie Insights Web | Add timepoint UI UX | AI-Web | Medium | Done | 2026-04-13 | 2026-04-20 | Closed
ACT-016 | Shared Platform | ⁠Sambataro K9 report | AI-Web | Medium | Done | 2026-05-12 | 2026-05-19 | Closed
ACT-017 | Shared Platform | Public API development | AI-Web | Medium | Done | 2026-05-12 | 2026-05-19 | Closed
ACT-018 | Shared Platform | ⁠API portal web - Self Service | AI-Web | Medium | In Progress | 2026-05-12 | 2026-05-19 | Overdue
ACT-019 | Annie Insights Web | API Report for Annie & Public Service | AI-Web | Medium | In Progress | 2026-05-12 | 2026-05-19 | Overdue
ACT-020 | Shared Platform | ⁠reporting API | AI-Web | Medium | Planned | 2026-05-21 | 2026-06-30 | On Track
ACT-021 | Shared Platform | preparing AI laptop u begin Fortran rewriting | AI-Web | Medium | In Progress | 2026-05-21 | 2026-06-30 | On Track
ACT-022 | Shared Platform | ⁠parallax | AI-Web | Medium | Blocked | 2026-05-21 | 2026-06-30 | On Track
ACT-023 | Shared Platform | Update login page content | AI-Web | Medium | Done | 2026-05-28 | 2026-06-04 | Closed
ACT-024 | Shared Platform | AI - On-screen tooth template rendering | AI-Web | Low | Blocked | 2025-05-27 | 2026-03-31 | Overdue
ACT-025 | Shared Platform | Can modify consult date | AI-Web | Low | Done | 2025-06-09 | 2025-06-16 | Closed
ACT-026 | Shared Platform | AI - VIP - submit form | AI-Web | Low | Done | 2025-08-25 | 2025-09-01 | Closed
ACT-027 | Executive Reporting | Strategic Product Ecosystem Analysis | Management | High | Done | 2026-06-01 | 2026-06-08 | Closed
ACT-028 | Shared Platform | CPS Future-State Workflow Framework | Management | High | Done | 2026-06-01 | 2026-06-08 | Closed
ACT-029 | Annie Insights Web | Source code takeover (90% complete) | AI-Web | Medium | In Progress | 2026-05-20 | 2026-06-15 | Due Soon
ACT-030 | Annie Insights Web | Deploy Angular and Backend Updates | AI-Web | Medium | Done | 2026-05-20 | 2026-06-10 | Closed
ACT-031 | Annie Insights Web | Auth0 Change Password Feature | AI-Web | Medium | Done | 2026-05-20 | 2026-06-10 | Closed
ACT-032 | Annie Insights Web | Popup Terms of Use & Privacy Policy | AI-Web | Low | Done | 2026-05-20 | 2026-06-10 | Closed
ACT-033 | Annie Insights Web | Birthdate & Age Validation | AI-Web | Medium | Done | 2026-05-20 | 2026-06-10 | Closed
ACT-034 | Annie Insights Web | UI/UX Bug Fixes | AI-Web | Medium | Done | 2026-05-20 | 2026-06-10 | Closed
ACT-035 | Annie Insights Web | Test Reporting Engine Buttons | AI-Web | Medium | Testing | 2026-06-10 | 2026-06-17 | Due Soon
ACT-036 | iSmartOffice Mobile App | Flutter Rewrite of iSmartOffice Clinic App | Mobile | High | In Progress | 2026-04-10 | 2026-06-30 | On Track
ACT-037 | iSmartOffice Web App | Appointment Status Sync to Clinic Calendar | Clinic-Web | High | In Progress | 2026-05-21 | 2026-06-15 | Due Soon
ACT-038 | iSmartOffice Mobile App | Implement Missing Dental Chart Parameters (Quadrant & Arch) | Mobile | Medium | In Progress | 2026-04-18 | 2026-05-30 | Overdue
ACT-039 | iSmartOffice Mobile App | Fix font-size clipping on 'I understand' button | Mobile | High | Done | 2026-04-26 | 2026-05-10 | Closed
ACT-040 | iSmartOffice Web App | Search Radius Customization for Specific GroupCodes | Clinic-Web | Medium | Done | 2026-04-25 | 2026-04-28 | Closed
ACT-041 | Infrastructure / DevOps | Dismantle IONOS & Migrate DNN and Provider DB to Azure | Infra | High | In Progress | 2026-05-06 | 2026-06-20 | Due Soon
ACT-042 | Infrastructure / DevOps | Migrate Jasper Reports to Azure | Infra | High | Done | 2026-05-06 | 2026-06-15 | Closed
ACT-043 | iSmartOffice Web App | Implement multi-assigned doctor selection in dental evaluation | Clinic-Web | Medium | Done | 2026-05-15 | 2026-05-21 | Closed
ACT-044 | iSmartOffice Web App | Reactivate OneSignal push notifications for iSmartOffice Clinic | Clinic-Web | Medium | In Progress | 2026-05-06 | 2026-06-10 | Overdue
ACT-045 | Infrastructure / DevOps | Restore and Recreate FMBODS@bioprogressive.org Email Account | Infra | Critical | Done | 2025-09-18 | 2025-09-19 | Closed

## HIGHLIGHTS TASKS LIST
Task ID | Product | Activity / Task | Team | Priority | Status | Start Date | Due Date
TASK-001 | Annie Insights Web | Fix and enhance Bulk upload image classifier | AI-Web | High | In Progress | - | -
TASK-002 | Annie Insights Web | ⁠link as much AI finding from Pano and dental upper and lower arches to dental chart auto fill | AI-Web | High | In Progress | - | -
TASK-003 | Annie Insights Web | enhance UIUX reporting in Annie especially the Treatment Sequence Gantt chart | AI-Web | High | In Progress | - | -
TASK-004 | Annie Insights Web | Add capability to use ANNIE in training mode | AI-Web | High | In Progress | - | -
TASK-005 | Annie Insights Web | parallax correction | AI-Web | High | In Progress | - | -
TASK-006 | iSmartOffice Web App | Language and currency | AI-Web | High | In Progress | - | -
TASK-007 | iSmartOffice Web App | fix all bugs in iOS and Android | AI-Web | High | In Progress | - | -
TASK-008 | iSmartOffice Web App | study the flow and proposal for CPS implementation which include the CareQuest grant application | AI-Web | High | In Progress | - | -
TASK-009 | Infrastructure | Dashboard Infrastructure | Collaboration | High | Done | - | -
TASK-010 | Collaboration (Pivot) | Dashboard User & Customer Support | Collaboration | High | In Progress | - | -
TASK-011 | Collaboration (Pivot) | Dashboard Team Report | Collaboration | High | In Progress | - | -
TASK-012 | Collaboration (Pivot) | Recreate Company Website | Collaboration | High | In Progress | - | -
TASK-013 | Collaboration (Pivot) | Recreate Company Product Sales Website ANNIE | Collaboration | High | In Progress | - | -
TASK-014 | Collaboration (Pivot) | Recreate Company Product Sales Website iSmartOffice | Collaboration | High | In Progress | - | -

## Personnel Weekly Report
Period | Tasks | Status | PIC
W1 July 2026 | Facelift mockup FMBO bioprogresive (Logo Update, Testimoni) | On Progress | Fikri
W1 July 2026 | Customer Support Dashboard | On Progress | Fikri
W1 July 2026 | Analysis Solution Architecture for CPS Dental Program | On Progress | Astrid
W1 July 2026 | Analysis Indonesia Market Entry Strategy | On Progress | Astrid
W1 July 2026 | Revisit patient app onboarding | On Progress | Astrid
W1 July 2026 | Redesign Booking Page iSmartOffice | On Progress | Rangga
W1 July 2026 | Redesign DR Annie Sales Landing Page | Done | Rangga
W1 July 2026 | Update page Team Report Dashboard | Done | Rangga
W1 July 2026 | Booking iSmartOffice, Sales Landing Page Annie & Team Report Dashboard Publication | On Progress | Rangga